## Sheet1
ISSUES FOR PIOLT DEPLOYMENT
Issue No | Activities | Assignee | Comments
#1344 | Issue in patient list for DemoDistrict-DemoFHC setup | Jiji | Login Failed. Invalid Login Credentials !!!
#1356 | Correct for incorrect entries in annotation table | jiji
#1357 | Resolve issues in database function for annotation storing from viewer state JSON | jiji
#1390 | Dashboard - FHC field alignment | jiji | District field alignment
#1413 | User managemnt | Jiji | user profile alignment
#1508 | Issue in back button click from report page | Jiji | The images are not shown in Fundus viewer upon clicking the back button from the report page
#1538 | in the excel, title may be given, can be name of the software . Generated/exported as on date | sreeshna
#1539 | Imageviewer - Page optimization | Jiji
#1543 | Imageviewer - Save Click -- image property annotations keeps changing | shameera
#1546 | Imageviewer - after save long page loading time | shameera
#1604 | Firefox browser -- Images not listing on top | shameera
#1619 | Settings menu - sub options displayed under Dashboard menu | shameera
#1648 | Change message of email failure | shameera
#1653 | Co located server email sending not working | shameera
#1655 | Image viewer - labels on annotations editable | shameera
#1660 | If only one FHC that can be selected by default | jiji | demouser login invalid
#1670 | Application takes more time to load so please clear the console print in browser. | jiji
#1681 | DB disconnection in between transaction -- Request header is too large error | jiji
#1682 | Patientlist Error -After clicking on the OptoleftFovea patient , then click TestpatRun named patient this error occurs | jiji

## Sheet2
ISSUES REPORTED BY KDISC
Issue No | Activities | Assignee | Comments
#1746 | All Tiles should be linked to the corresponding patient worklist | Jiji
#1747 | Sensitivity and Specificity should be linked to corresponding patient work list | Jiji
#1751 | Email – To send the Email again in the future | Jiji
#1752 | Send email option is not working | Jiji
#1754 | No listing for specificity and sensitivity | Jiji
#1755 | Data error in all Tilles in Dashboard and not getting redirected to respective tiles | Jiji | Error in analysis status/ Count of Submitted is not listed anywhere - currently Submitted ones are listed in Pending List
#1758 | Date Filter required in admin login for patient list | Jiji
#1760 | Remove The Forward Option in Image Viewer in RIOT user.(Dropdown is empty) | Jiji
#1761 | If status is submitted by RIOT User , The analysis status to be submitted in all the roles. | Jiji
#1763 | User Management- Search using Doctor is possible only if Salutation is provided correctly. | Jiji
#1764 | Remove The Forward Option in Image Viewer | Jiji
#1765 | Reset password in settings not working . | Jiji
#2151 | Issue in sensitivity and specificity calculation | shameera
#2152 | Issue in UHID linking through direct and fallback mechanisms | shameera | The patient images sent through direct and fallback mechanisms are treated as different
#2153 | Delay in displaying dashboard and patient list -- SDC deployed application | shameera
#2154 | Issue in mapping of annotation and corresponding lesion | shameera