## DR Application Review -CDAC
DR - Web Application - Review
Sl No |  | Issues | Status as of 21.11.2023 | Remarks
1 | H0ME PAGE (Optometrist - TVM User) | Application is Slow while filtering data | Resolved | In Observation
2 |  | All Tiles should be in same size | Resolved
3 |  | Apply Button for date selection - Move to right side of date filter | Resolved
4 |  | Patient work list - Add one column for serial number | Pending | Serial numbers are incorrect in subsequent pages.
5 |  | While clicking on UHID , page is refreshing and it moves to the top of the page, we have to scroll down to see the patient details | Resolved
6 |  | Date Range filter should keep last 7 days as default in page load | Resolved
7 |  | Patient work list should only show for the selected date range | Resolved
8 |  | All Tiles should be linked to the corresponding patient worklist | Pending
9 |  | Data error in all Tilles in Dashboard | Pending | Error in analysis status/ Count of Submitted is not listed anywhere - currently Submitted ones are listed in Pending LIst
10 |  | Sensitivity and Specificity should be linked to corresponding patient work list | Pending
11 |  | FHC filtering Should be included in the dashboard filters | Resolved
12 |  | Age ,Patient Name, UHID, Analysis Status to be included in search | Resolved
13 |  | Patient Work list - Change the table format - Sl No,Date created,,FHC name,UHID, Patient name, Age ,Analysis status | Resolved
14 |  | Export to excel option needed from the patient worklist to export the selected data in the worklist | Pending | The heading shows date in yyy-mm-dd format. Change to dd-mm-yyyy
15 |  | Analysis Status for the records - New, Reviewed, Submitted, Forwarded | Pending | Once submitted analysis status should not be editable. Atleast one image to be viewed mandatorily before marking as reviewed.
16 | FUNDUS VIEWER ( All Roles) | Clicking Back on the browser from the Image view page logs out the application . It should go back to the Dashboard page. | Pending | By Clicking on the Back Button of the browser user should be taken to the previous page with the selected Filters.BACK button is currently disabled.
17 |  | Manual Report Section should be brought to the right side. | Resolved
18 |  | Automated Report Section should be moved to the left side. | Resolved
19 |  | Forward functionality is not working in trial user | Resolved
20 |  | Reset function works only for Zoom/Pan - Need to rearrage RESET button | Resolved
21 | REPORT PAGE (All Roles) | Save – Should save the record. | Resolved
|  | Submit – Should Save and Email. Show message as ‘Email Sent’ after sending the email. Once submitted, the Save and Submit buttons should disappear. | Resolved
|  | Email – To send the Email again in the future | Pending | To check internally (K-DISC)
|  | Print – To Print in the future | Resolved
|  | Back – Always present on the page – To back to previous page. | Resolved
22 |  | Send email option is not working | Pending
23 |  | Correct the time displayed in the report in to IST | Pending | Incorrect Time in Report while printing
24 | ADMIN USER | No listing for specificity and sensitivity | Pending
25 |  | Data error in all Tilles in Dashboard and not getting redirected to respective tiles | Pending | Error in analysis status/ Count of Submitted is not listed anywhere - currently Submitted ones are listed in Pending LIst
26 |  | No of pending cases and no of cases captured is not shown in tiles | Pending | Submitted cases also appeared in pending
27 |  | Not able to view the images from ADMIN login so unable to test further | Resolved
28 |  | Date Filter required in admin login for patient list | Resolved
Additional Findings
29 | RIOT User | The RIOT/Ophthalmologist should be able to see all records using the filters in dashboard, similar to the Admin in addition to the cases forwarded from the Optometrist by default while logging in. | Pending
30 |  | Remove The Forward Option in Image Viewer in RIOT user.(Dropdown is empty) | Pending
31 |  | If status is submitted by RIOT User , The analysis status to be submitted in all the roles. | Pending
32 | FUNDUS VIEWER ( All Roles) | Refresh button in the Image View Page takes the user back to Dashboard page | Pending
33 | ADMIN USER | User Management- Search using Doctor is possible only if Salutation is provided correctly. | Pending
34 |  | Remove The Forward Option in Image Viewer | Pending
35 |  | Reset password in settings not working . | Pending